## Sheet1
Risk Assessment
Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
The developer falls ill | The project will not be completed on time | Low | High | N/A | Request an extension | Increase level of hygiene practices
The JUnit tests fail | The API will not work as desired | High | Medium | Developer | The code in the program and the test code need to be checked for mistakes and corrected | Ensure test code is correctly written whilst it is being written and test the functionality of new methods as they are written to identify mistakes in code before testing
Unit and integration tests don’t reach 80% test coverage | Lower project mark | Medium | Medium | Developer | Contact trainers for advice to increase test coverage | Carry out self study and research to increase knowledge of testing
The project is not completed in time | Potential to fail the project | Low | High | Developer | Request an extension | Manage time taken on tasks appropriately and keep well organised
The full requirements of the project brief have not been achieved | Lower project mark | Low | Medium | Developer | Read project brief to identify missed requirement and inckude it in your project submission ASAP | Create stories and tasks on the project jiraboard based on each project brief requirement and set these to highest priority
Connection to the database can't be established | The CRUD requests will fail | Low | High | Developer | View recorded lectures to follow step-by-step instructions to identify mistake, or contact trainers for guidance | Solidify knowledge on connecting the database or follow step-by-step tutorial in recorded lectures if unsure
Frontend and Backend are not linked correctly | The user will not be able to access the backend functionality | High | High | Developer | View recorded lectures to follow step-by-step instructions to identify mistake, or contact trainers for guidance | Solidify knowledge on linking the Frontend and Backend or follow step-by-step tutorial in recorded lectures if unsure
The JUnit tests fail
Unit and integration tests don’t reach 80% test coverage
The full requirements of the project brief have not been achieved
Frontend and Backend are not linked correctly
The developer falls ill
The project is not completed in time
Connection to the database can't be established
High
Medium
Low
Medium
Low
High
Risk Assessment Matrix
Impact Level
Likelihood